## Sheet1
TASK NAME | TASK ID | ASSIGNEE | COMMENTS | JUSTIFICATION | ACTION | START DATE TIME | END DATE TIME | TAGS | PRIORITY | MARK DATE
Analytics Layout | 86eqgxq8h | Mohammad Ibrahim |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-16 17:00:00 | mark 1 | HIGH
Implement Unread Message Tracking for Each Agent Separately | 86eqmtumj | Osaid Zaatreh |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-31 17:00:00 | mark 1 | NORMAL
Test OMS design issues 5 | 86eqgwzwf | Layan Lafi |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-17 17:00:00 | mark 1 | NORMAL
Implement Unread Message Tracking for Each Agent Separately | 86eqmtumj | Osaid Zaatreh |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-31 17:00:00 | mark 2 | NORMAL
Agents Performance | 86eq9f4mw | Mohammad Ibrahim |  | Not Justified |  | 2024-10-10 08:00:00 |  | mark 1 | HIGH
Test Issues in I-Step Desk | 86eqmf1fq | Layan Lafi |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-31 17:00:00 | mark 1 | NORMAL
Fix issues in the main gate system | 86eqjb0xz | Osaid Zaatreh |  | Not Justified |  | 2024-10-22 08:00:00 | 2024-10-22 17:00:00 | mark 1 | NORMAL
Capturing Tool | 86eqgztqb | Rawan Morad |  | Not Justified |  | 2024-10-24 08:00:00 | 2024-10-24 17:00:00 | mark 1 | HIGH
Generate Attendance Report | 86eqgztq9 | Rawan Morad |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-23 17:00:00 | mark 1 | HIGH
Capturing Tool | 86eqgzqyy | Osaid Zaatreh |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-23 17:00:00 | mark 1 | HIGH
Dashboard | 86eqgzqyx | Osaid Zaatreh |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-23 17:00:00 | mark 1 | HIGH
Generate Attendance Report(1) | 86eqgzqyq | Osaid Zaatreh |  | Not Justified |  | 2024-10-20 08:00:00 | 2024-10-20 17:00:00 | mark 1 | HIGH
Meeting To - with Careem team (Quality manager- Sally) to check the Quality supervisor privilege – (Reports, and ticket’s Design) | 86eqjgreu | Dana |  | Not Justified |  | 2024-10-23 10:00:00 | 2024-10-23 18:00:00 | mark 1 | NORMAL
Fix issues in the Recording system | 86eqjga7b | Osaid Zaatreh |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-23 17:00:00 | mark 1 | NORMAL
Skill Groups | 86eqbn18b | Abdallah Rawashdeh |  | Not Justified |  | 2024-10-07 08:00:00 | 2024-10-27 17:00:00 | mark 1 | NORMAL
User Groups | 86eqbn18a | Abdallah Rawashdeh |  | Not Justified |  | 2024-10-06 08:00:00 | 2024-10-27 17:00:00 | mark 1 | NORMAL
User Management | 86eqbn185 | Abdallah Rawashdeh |  | Not Justified |  | 2024-10-01 08:00:00 | 2024-10-21 17:00:00 | mark 1 | NORMAL
Resolve Issues in I-Step Desk | 86eqmf14c | Osaid Zaatreh |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-30 17:00:00 | mark 1 | NORMAL
Add Email Filtering to All Users Reports | 86eqm4wkn | Osaid Zaatreh |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-30 17:00:00 | mark 1 | NORMAL
Revise Quality Dashboard to Filter Agents by Level (Catalogue, Studio, Quality) | 86eqm4vrv | Osaid Zaatreh |  | Not Justified |  | 2024-10-29 08:00:00 | 2024-10-30 17:00:00 | mark 1 | NORMAL
Fix The Evaluation Reports Issue On The I-Step Desk | 86eqktvt5 | Osaid Zaatreh |  | Not Justified |  | 2024-10-28 08:00:00 | 2024-10-28 17:00:00 | mark 1 | NORMAL
Create Quality Dashboard on I-Step Desk | 86eqju02h | Osaid Zaatreh |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-24 17:00:00 | mark 1 | HIGH
Fix The Design Issue On The I-Step Desk | 86eqjkm05 | Osaid Zaatreh |  | Not Justified |  | 2024-10-24 08:00:00 | 2024-10-28 17:00:00 | mark 1 | NORMAL
Fix issues in the I-Step System | 86eqjjx6f | Osaid Zaatreh |  | Not Justified |  | 2024-10-23 08:00:00 | 2024-10-23 17:00:00 | mark 1 | HIGH
Analytics Left Side | 86eqgxq8m | Osaid Zaatreh |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-17 17:00:00 | mark 1 | HIGH
Generate Evaluation Report | 86eqgxq2q | Osaid Zaatreh |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-16 17:00:00 | mark 1 | HIGH
Update {Comment, Fields, Status} | 86eqdkztp | Abdullah Al-Kurdi |  | Not Justified |  | 2024-10-17 09:00:00 | 2024-10-17 18:00:00 | mark 1 | NORMAL
Fetching Api’s {Tickets , Status, Comments} | 86eqdkztg | Abdullah Al-Kurdi |  | Not Justified |  | 2024-10-14 09:00:00 | 2024-10-16 18:00:00 | mark 1 | NORMAL
Resolve Issues with Ticket Category Filter | 86eqgjm6v | Osaid Zaatreh |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-16 17:00:00 | mark 1 | NORMAL
Implement Password Reset with Unique Passwords - QA | 86eqa911j | Rawan Morad |  | Not Justified |  | 2024-10-28 08:00:00 | 2024-10-31 17:00:00 | mark 1 | NORMAL
Change Canned Responses to Laravel Excel | 86eqgxpt5 | Mohammad Ibrahim |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-16 17:00:00 | mark 1 | HIGH
Features to implement from I-Desk- Dashboards | 86eq82m7w | Osaid Zaatreh |  | Not Justified |  | 2024-10-29 08:00:00 | 2024-10-31 17:00:00 | mark 1 | NORMAL
Study the dashboard KPIs and APIs | 86eq82m7v | Osaid Zaatreh |  | Not Justified |  | 2024-10-27 08:00:00 | 2024-10-28 17:00:00 | mark 1 | NORMAL
General Check on OMS | 86eqjtemd | Layan Lafi |  | Not Justified |  | 2024-10-30 08:00:00 | 2024-10-30 17:00:00 | mark 1 | NORMAL
General Check on OMS | 86eqh4m7p | Layan Lafi |  | Not Justified |  | 2024-10-17 08:00:00 | 2024-10-17 17:00:00 | mark 1 | NORMAL
General Check on OMS | 86eqgnjn3 | Layan Lafi |  | Not Justified |  | 2024-10-16 08:00:00 | 2024-10-16 17:00:00 | mark 1 | NORMAL
Meeting To - discuss the quality dashboard requirements | 86eqj2wy6 | Dana |  | Not Justified |  | 2024-10-21 15:00:00 | 2024-10-21 18:00:00 | mark 1 | NORMAL
Meeting To - follow up on the project plan status | 86eqh60bw | Dana |  | Not Justified |  | 2024-10-17 12:00:00 | 2024-10-17 17:00:00 | mark 1 | NORMAL
Meeting To - demo for quality team | 86eqgyw3v | Dana |  | Not Justified |  | 2024-10-16 13:00:00 | 2024-10-16 18:00:00 | mark 1 | NORMAL
Evaluation Session For Sep - Tickets - Osaid | 86eqjaegj | Osaid Zaatreh |  | Not Justified |  | 2024-10-28 12:30:00 | 2024-10-28 17:00:00 | mark 1 | LOW
Evaluation Session For Sep - Tasks - Dana | 86eqjaeg7 | Dana |  | Not Justified |  | 2024-10-22 13:00:00 | 2024-10-22 18:00:00 | mark 1 | LOW
Evaluation Session For Sep - Tasks - Osaid | 86eqjaeg3 | Osaid Zaatreh |  | Not Justified |  | 2024-10-22 14:30:00 | 2024-10-22 17:00:00 | mark 1 | LOW
Weekly Update The Progress Of The Project Plans On Zoho | 86eqjxzk2 | Dana |  | Not Justified |  | 2024-10-27 09:00:00 | 2024-10-31 18:00:00 | mark 1 | NORMAL
Weekly Update The Progress Of The Project Plans On Zoho | 86eqh824a | Dana |  | Not Justified |  | 2024-10-20 09:00:00 | 2024-10-24 18:00:00 | mark 1 | NORMAL
Survey document | 86eqkv14w | Dana |  | Not Justified |  | 2024-10-28 09:00:00 | 2024-10-28 18:00:00 | mark 1 | NORMAL
Changes on the Survey document | 86eqj95fh | Dana |  | Not Justified |  | 2024-10-22 09:00:00 | 2024-10-22 18:00:00 | mark 1 | NORMAL
Create a document for the Survey module | 86eqgje2f | Dana |  | Not Justified |  | 2024-10-15 09:00:00 | 2024-10-21 18:00:00 | mark 1 | NORMAL
Test the quality evaluation | 86eqkj9yd | Dana |  | Not Justified |  | 2024-10-28 09:00:00 | 2024-10-29 18:00:00 | mark 1 | NORMAL
Check the I-Step Functionality | 86eqjh1u9 | Dana |  | Not Justified |  | 2024-10-23 09:00:00 | 2024-10-24 18:00:00 | mark 1 | NORMAL
Meeting To - To Discuss NWC API’s, and to do logs API. | 86eqj1w6f | Hasan Takrory |  | Not Justified |  | 2024-10-21 15:00:00 | 2024-10-21 17:00:00 | mark 1 | NORMAL
Meeting To - Ajex Migration | 86eqh5zg6 | Abdullah Al-Kurdi |  | Not Justified |  | 2024-10-17 11:00:00 | 2024-10-17 18:00:00 | mark 1 | NORMAL
Meeting To - Discuss the new project (ISP) and determine the estimated time and duration for each task. | 86eqdcpz1 | Rawan Morad |  | Not Justified |  | 2024-10-01 15:30:00 | 2024-10-01 17:00:00 | mark 1 | NORMAL
Meeting To - Discuss the new project (ISP) and determine the estimated time and duration for each task. | 86eqdcpz1 | Dana |  | Not Justified |  | 2024-10-01 15:30:00 | 2024-10-01 17:00:00 | mark 1 | NORMAL
Test Task - Abdalgani | 86eqt5egn | Abdalgani |  | Not Justified |  | 2024-11-19 08:00:00 | 2024-11-20 17:00:00 | mark 1 | NORMAL
RFC 2918 | 86equf8d0 | Abdullah Al-Kurdi |  | Not Justified |  | 2024-11-21 09:00:00 | 2024-11-21 18:00:00 | mark 1 | NORMAL
RFC 2901 | 86equf8a4 | Abdullah Al-Kurdi |  | Not Justified |  | 2024-11-21 09:00:00 | 2024-11-21 18:00:00 | mark 1 | NORMAL
Fix issue in users management design (Layan’s Email - attached) | 86eqv3534 | Mohammad Ibrahim |  | Not Justified |  | 2024-11-26 08:00:00 | 2024-11-26 17:00:00 | mark 1 | NORMAL
Users Management | 86equptwg | Mohammad Ibrahim |  | Not Justified |  | 2024-11-20 08:00:00 | 2024-11-20 17:00:00 | mark 1 | NORMAL
Fetch User Groups, Skills | 86equptwb | Mohammad Ibrahim |  | Not Justified |  | 2024-11-19 08:00:00 | 2024-11-19 17:00:00 | mark 1 | NORMAL
Setup the Testing Server and GitHub | 86equptw9 | Mohammad Ibrahim |  | Not Justified |  | 2024-11-18 08:00:00 | 2024-11-18 17:00:00 | mark 1 | NORMAL